[YOUR BUSINESS NAME]

Your Event Timeline

Sent [7 days / 48 hours] before your event. Reply "Confirmed" or tell us what changed.

| Event | [Event name] ¦ [Date] |
| --- | --- |
| Location | [Venue, address] |
| Guest count | [Final number] |
| Your on-site contact | [Name, phone] |
| Our event lead | [Name, phone] |

| TIME | WHAT HAPPENS | WHO |
| --- | --- | --- |
| [3:30 PM] | Our team arrives and checks in at [entrance] | [Event lead] |
| [3:45 PM] | Setup begins: tables, displays, hot holding | Our team |
| [4:45 PM] | Food set and ready; temperature check | Our team |
| [5:00 PM] | Quick walkthrough with you (5 minutes) | You + event lead |
| [5:30 PM] | Service begins | Our team |
| [7:00 PM] | Service ends; desserts and coffee stay out | Our team |
| [7:15 PM] | Breakdown begins in food areas | Our team |
| [7:45 PM] | Final walkthrough; we're out | Event lead |

| MENU (FINAL) | DIETARY AND ALLERGY NOTES |
| --- | --- |
| [Item 1] [Item 2] [Item 3] [Item 4] [Item 5] | [e.g. 6 vegetarian, 2 gluten-free, 1 nut allergy] All allergen items labeled at the buffet [Separate plates prepared for: ] |

PLEASE CONFIRM

☐ Guest count is final ☐ Timeline works with the venue and your program ☐ On-site contact name and phone are correct ☐ Dietary notes are complete Reply "Confirmed" or call [phone] with any changes by [date].

MODULE 3 TEMPLATE

How to Use the Timeline

Page 1 goes to the client.

The timeline confirmation is the last chance to catch a problem before it becomes an event-day surprise. It also shows the client you have a plan, which lowers their anxiety and the number of "just checking" calls you get.

## When to Send

| EVENT TYPE | SEND |
| --- | --- |
| Corporate drop-off or lunch | 48 hours before |
| Staffed corporate event | 5-7 days before |
| Weddings and large private events | 7-10 days before, then a 48-hour check-in |

## Tips

- Build the times backward from service start, the same way your Route & Load Planner does (Catering Profit System, Module 4).

- Coordinate with the venue's load-in rules before you send it. Planners will catch it if you don't.

- Copy the planner or venue coordinator when there is one. It makes you look organized to your referral partners too.

- No reply in 24 hours? Call. Silence on a timeline is how surprises happen.